## April 1
|  |  | Weekly Sprint Sheet |  | Team Members | Email
Project: 5 |  |  |  |  | Jordan Chen | jchen292@uic.edu
Week Of: April 29 - May 3, 2019 |  |  |  |  | Bryan Nguyen | bnguye39@uic.edu
[5 empty] | Edgar Camacho | edgarc2@uic.edu
[5 empty] | Juan Guiterrez | jgutie61@uic.edu
Action Item | Item ID | Team Member | Last Week | This Week | Next Week | Issues
Game Logic | 1 | Juan Guiterrez | Start deciding how game will be played out | Worked around with map border and images | Add obstacles and power ups
Configuring game scenes and adding addition features | 2 | Jordan Chen | Decide how Tank will function in game | Worked around with game bonuses | debug
Networking features and connection between server and Clients | 3 | Edgar Camacho | Start Server for Game | Write Game Logic Code | Game appearance
GUI elements and Enchancing certain elements | 4 | Bryan Nguyen | Create ideas for how the GUI and user interface will look like | Worked with player and bullet objects | Lobby and Start-up appearance